## Sheet1
Xero Application
|  |  | Test Cycle 1 | Test Cycle 2 | Test Cycle 3
Application Modules | Feature Backlog | Story Points | Execution ends - April 19 | Execution ends - May 3 | Execution ends - May 10
Module 6 - Invoicing | 06.01 Create new invoices | 3 | x
| 06.02 Create recurring invoices | 4 | x
| 06.03 Change existing invoices | 5 | x
| 06.04 Submit existing invoices | 3 | x
| 06.05 Approve existing invoices | 3 | x
| 06.06 Delete existing invoices | 3 | x
| 06.07 Customize invoices | 3 | x
| 06.08 Create new credit notes | 1 | x
| 06.09 Configure invoice reminders | 4 | x
| 06.10 View invoice draft | 1 | x
| 06.11 View awaiting approval invoices | 2 | x
| 06.12 View paid invoices | 2 | x
| 06.13 View repeating invoices | 1 | x
| 06.14 Manage customers | 3 |  | x
| 06.15 Integrate online payments | 3 |  | x
| 06.16 Handle taxes on invoices | 3 |  | x
| 06.17 Track invoices & status updates | 1 |  | x
| 06.18 Import/export invoices | 3 |  | x
Module 7 - Account Receivables | 07.01 Set up payment | 5 |  | x
| 07.02 Create new Quotations | 4 |  | x
| 07.03 Accept Quotations | 3 |  | x
| 07.04 View Accepted Quotations | 3 |  | x
| 07.05 View Invoiced Quotations | 2 |  | x
| 07.06 Conversion of Quotations to Invoices | 3 |  | x
| 07.07 Add Quotation Notes | 3 |  | x
| 07.08 Create Statements | 5 |  |  | x
| 07.09 Filter Statements | 3 |  |  | x
| 07.10 Create Aging Reports | 5 |  |  | x
| 07.11 Export Aging Reports | 4 |  |  | x
| 07.12 Complete Bank Account Reconciliations | 5 |  |  | x
| 07.13 Edit customer Contact Details | 1 |  |  | x
| 07.14 Edit customer Financial Details | 1 |  |  | x
| 07.15 Set customer credit limits | 5 |  |  | x
| 07.16 Manage payment terms | 4 |  |  | x
|  | VELOCITY: | 35 | 36 | 33